A Vision for Public Engagement

Maximize Impact in Raising Awareness of AI Risks

All section titles link to the full interactive presentation

The AI Risk Spectrum Interactive visualization of where the public stands on AI risk

Who Thinks What? : The Dismissive · The Unconcerned · Cautiously Optimistic · Concerned (Current) · Concerned (Future) · The Alarmed.

The Conversion Funnel: Lethal Intelligence sits high in the funnel – generating members for Humans First action.

Goals

Goal 1: Change the Shape of the Curve — Shift public perception. Move the distribution mass rightward.

Goal 2: Risk Awareness Force — Self-feeding hypergrowth loop – create an “army“ of preachers.

Why Grassroots Change Matters — Politicians lead from behind. Grassroots demand creates the leaders we need.

Perceptions Disconnect

TPOT (This Part of Twitter) — Filter bubble that vastly overestimates how much the public understands AI risk.

AI Safety Community — Seen as conspiracy theorists by the general public. Massive communication chasm.

Strategies

Three priorities: Organic Growth (each converter becomes a broadcaster) · Cross-Pollinate Distribution (reuse proven viral content) · Build In-House Muscle (internal creators and managers).

The Engagement Trade-Off

- — Meet people where they are:  Audiences high in the funnel are hit with memes and clips, gradually further down get exposed to deeper truth, more complex concepts, more cacademic accuracy.

Strategy Execution Plan

| Area | Goal / Aim | Resources | Budget | Timeline | Dependencies |
| --- | --- | --- | --- | --- | --- |
| Distribution Pipeline | Scale ~9M views/mo → ~9M/week | 2 initial (creator + broadcaster); scale to 2-3 broadcasters/creator, up to 12 for 3 creators | Creator: $3-4K/mo Broadcaster: $500-800/mo | 4 weeks after tech build | Technical infrastructure |
| Platform Expansion (beyond Reddit) | Adapt viral content natively per platform | 1 dedicated adaptation resource | ~$1,200/mo | Alongside pipeline | Pipeline operational |
| Community | Build community; grow volunteers, fans, organic traffic | 1 engagement resource | ~$1,200/mo | Ongoing | — |
| Takedowns | Systematic counter-arguments to AI risk denial | 1 producer (TBD) video-editor time | TBD | After March 2026 | All above operational |

Scaling: Add broadcasters incrementally per creator (2→3→…→12), scaling output indefinitely. Budget note: All estimates provisional, subject to revision with real-world data.

Distribution Engine

Current: ~9M views/month → Target: ~9M/week → No hard ceiling.

Resonance Intelligence — Track what works, where, and for whom across communities.

Production Pipeline — Content Intelligence → Variation Creation → Queue System → Targeted Distribution.

r/AIDangers — 0 → 30K members in 6 months. Goal: 1M by end of 2026.

The Hub — lethalintelligence.ai

One-stop destination for AI risk awareness. Fills two gaps: no place to just read and no place to find & share. Content: Magazine · Luminary Clips · Meme Archive · Microblog · Open Letters · Action Paths.

The Conversion Journey

Infiltration → Immersion → Evidence → Conversion → Activation. Self-driven immersion creates unstoppable motivation.

Content & Reach

YouTube & Animation — Animated film on AI risk + podcast and short-form content engine.

Wild Experiments — No Plot Armor · 2030 · Reality is Broken · Dystopian Intelligence — four experimental content formats.

Influencer Deals — Niche partnerships: Transportation (automation) · Education (career crisis) · Software Engineering (AI coding).

The Concerned Split

Even among the concerned: Current risks (job loss, surveillance) vs. Future risks (bioterrorism, power concentration) vs. Alarmed (loss of control, extinction). The fault line lies between 'concerned about current' and 'alarmed about future.'

Where Do We Go From Here?

Mission: Influence the shape of the curve, before it's too late. This will be the most decisive factor of what version of the future we land on.